## Light
Assessing Electric Transportation Options For USM Campuses
EGN 304 SL Project |  |  |  |  | Legend: | On track |  |  |  |  | Low risk |  |  |  |  | Med risk |  |  |  |  | High risk |  |  |  |  | Unassigned
Mackenzie F Libby
Project Start Date: | 2021-06-09 |  |  |  |  | June | [27 empty] | July
Scrolling Increment: | 0 | time axis 2021-06-09 to 2021-08-03
Milestone description | Category | Notes | Progress | Start | Days | time axis 2021-06-09 to 2021-08-03
Data Compilation | High Risk | Tasks concerning data collection, analysis, etc | 100% | 2021-06-09 | 54
Cost Structure | High Risk | Costs of project (vans, buses, solar panels, etc) | 100% | 2021-06-09 | 54
Charging Station | High Risk | Specifics concerning charging stations. Power requirements, time to full charge, etc | 100% | 2021-06-09 | 54
Route Analysis | Med Risk | Data on routes that may be taken with the vehicles, for cost and options | 100% | 2021-07-09 | 12
Industry Investigation | Low Risk | Investigate what other people have done to solve a similar issue (NEVER REINVENT THE WHEEL) | 100% | 2021-07-14 | 19
Miscellaneous | On Track | Other data that becomes relevant along the way | 100% | 2021-06-09 | 54
Options Breakout | High Risk | Structuring of all reasonable options | 100% | 2021-06-09 | 54
PV Panel Locations | High Risk | Possible locations for solar panels to be placed, and the relative costs/conditions for such placements | 100% | 2021-06-24 | 20
Vehicle Type | Med Risk | Collection of vehicle options, i.e. models, specifications, etc | 100% | 2021-06-24 | 7
Route Optimization | Low Risk | Which, if any, routes are the best for other options | 100% | 2021-06-29 | 30
General | Milestone | General compilation of options (report) | 100% | 2021-07-29 | 1 | bar: 2021-07-29
Other | Goal | Other relevant options | 100% | 2021-07-28 | 1 | 2021-07-28: 2
Communiques | Med Risk | People who it may be beneficial to talk to, once some of the above tasks are completed/well underway | 100% | 2021-06-09 | 68
TK | On Track | Service Learning | 0% | 2021-06-24 | 45
Trane | On Track |  | 0% | 2021-06-24 | 45
Aaron Withham | On Track | Host Site Surpervisor | 0% | 2021-06-24 | 45
Chris Brook | On Track | Competative Energy | 0% | 2021-06-24 | 45
Pre-existing network | On Track | Other people already in my network may also be useful resources | 0% | 2021-06-24 | 45
Reporting | High Risk | Final/Progress Reports | 74% | 2021-06-09 | 68
Progress Report 1 | Milestone |  | 100% | 2021-06-27 | 1 | bar: 2021-06-27
Progress Report 2 | Milestone |  | 100% | 2021-07-18 | 1 | bar: 2021-07-18
Final Progress Report | Milestone |  | 60% | 2021-08-01 | 1
Project Report | Milestone |  | 60% | 2021-08-15 | 1
Video Presentation | Milestone |  | 50% | 2021-08-15 | 1 | bar: 2021-08-01
To add more data, Insert new rows ABOVE this one